## Instructions
FixedLending — Scope of Work (SOW) Template — Instructions
How to Use
1) Go to 'Blank Template'. Fill in cost for EACH line that applies. 2) Add clear Notes for brands/finishes (e.g., 'LVP 20mil wear layer'). 3) Draws: Enter dollar amounts in Draw #1–#5 per line item or leave blank and use the category-level guidance in the Example tab. 4) Category Summary (top-right) totals each trade and computes a 10% contingency + estimated total. 5) Review: Ensure no critical cells are blank. Keep the scope within the approved budget.
Common Misses to Avoid
• Demo forgetting haul-off/final clean • Electrical/plumbing trim-out not included • Roof venting/pipe boots omitted • Kitchen missing backsplash, sink/faucet, or appliance install • Window quotes excluding interior trim/paint • Siding repairs without paint • Concrete/driveway patch scope too small • Door/trim without hardware budget
Draw Request Guidance
Typical draw pacing by completion stage: Draw1≈20% (demo/startup), Draw2≈25% (rough‑ins), Draw3≈25% (drywall/prime), Draw4≈20% (interior finishes), Draw5≈10% (punch/landscaping). Enter the DATE under each draw header. You may allocate draws per line item (columns Draw #1–#5) or by category total; see Example tab for a filled model.
Submission Checklist
☐ Property header complete (Address, Borrower, Contractor, SF, Version/Date) ☐ Invoice detail matches lines items being requested ☐ Category subtotals non‑zero • Contingency at least 10% • Total within approved budget ☐ Draw #1–#5 amounts planned and draw DATEs filled ☐ Final PDF/Excel submitted prior to closing

## Example (Filled)
FixedLending — Scope of Work (Example — ~$85K Rehab with Draw Plan)
Property Address | 123 Main St |  |  | Category Summary
Borrower Name | John Doe |  |  | Demo & Prep | 5000
Contractor Name |  |  |  | Foundation / Structure | 6500
Project Type (Cosmetic/Light/Full) | Full |  |  | Roof & Exterior | 21100
Total SF | 2300 |  |  | Interior Finishes | 14300
Rehab Budget Target | 85000 |  |  | Kitchen | 10000
Scope Version | V.1 |  |  | Bathrooms | 11200
Date Reviewed | 2025-10-17 |  |  | Mechanical Systems | 14500
Approved By | Ryan Kadlec |  |  | Landscaping & Curb Appeal | 2400
|  |  |  | Subtotal (All Categories) | 85000
|  |  |  | Contingency (10%) | 8500
|  |  |  | Estimated Total | 93500
Category | Item | Total | Notes | Draw #1 | Draw #2 | Draw #3 | Draw #4 | Draw #5
|  |  |  | Date | Date | Date | Date | Date
Demo & Prep
Demo & Prep | Interior demo (walls/floors/cabs) | 3500 | Include haul-off & cleanup
Demo & Prep | Dumpster & haul-off (30-yd) | 1000 | Two pulls typical
Demo & Prep | Site cleanup / final broom | 500 | Before final walk
Foundation / Structure
Foundation / Structure | Foundation leveling/spot piers | 3000 | Bid required if cracks/doors stick
Foundation / Structure | Structural beam/sill repair | 0 | As needed
Foundation / Structure | Framing (interior/exterior walls) | 0 | New/repair framing
Foundation / Structure | Drywall install/finish | 2000 | Hang, tape, mud, texture
Foundation / Structure | Insulation (walls/attic) | 1500 | Batt or blown-in
Roof & Exterior
Roof & Exterior | Roof tear-off & replace (30-yr) | 10000 | Ice/water shield, vents
Roof & Exterior | Gutters & fascia repairs | 1000 | Downspouts included
Roof & Exterior | Exterior paint incl. trim | 4500 | Prep, caulk, doors
Roof & Exterior | Window replacements (vinyl DP) | 3000 | Includes install & trim
Roof & Exterior | Siding repair/replacement | 0 | Replace damaged sections
Roof & Exterior | Concrete/driveway repair or replacement | 1500 | Patches or new panel
Roof & Exterior | Garage door replace/install | 1100 | Includes opener & trim
Interior Finishes
Interior Finishes | LVP flooring install | 4000 | Luxury vinyl plank
Interior Finishes | Tile flooring install | 1000 | Kitchen/entry
Interior Finishes | Carpet install | 1000 | Bedrooms/basement
Interior Finishes | Interior paint walls/trim/ceilings | 4000 | SW Promar 200
Interior Finishes | Doors/trim install | 2000 | Interior doors and casing
Interior Finishes | Hardware package | 800 | Handles, hinges, locks
Interior Finishes | Lighting package (fans/cans/vanity) | 1500 | Per plan
Kitchen
Kitchen | Cabinets + install (shaker) | 3500 | Soft-close if budget allows
Kitchen | Countertops (quartz) + backsplash | 3000 | Undermount sink cut
Kitchen | Sink + faucet set | 500
Kitchen | Appliance package (4pc) | 3000 | Range, MW, DW, fridge
Bathroom #1
Bathrooms | Bathtub | 2000
Bathrooms | Shower pan | 0
Bathrooms | Flooring | 1000
Bathrooms | Vanity/Sink | 1200
Bathrooms | Toilet | 700
Bathrooms | Fixtures/Finishes | 1000
Bathroom #2
Bathrooms | Bathtub | 0
Bathrooms | Shower pan | 2000
Bathrooms | Flooring | 800
Bathrooms | Vanity/Sink | 800
Bathrooms | Toilet | 700
Bathrooms | Fixtures/Finishes | 1000
Bathroom #3
Bathrooms | Bathtub | 0
Bathrooms | Shower pan | 0
Bathrooms | Flooring | 0
Bathrooms | Vanity/Sink | 0
Bathrooms | Toilet | 0
Bathrooms | Fixtures/Finishes | 0
Mechanical Systems
Mechanical Systems | HVAC system (3-ton) replace/serv | 7500 | Duct as needed
Mechanical Systems | Electrical panel/rough/finish | 3500 | Include CO/SMK detectors
Mechanical Systems | Plumbing rough/trim + WH | 3500 | 50-gal WH, lines, stops
Landscaping & Curb Appeal
Landscaping & Curb Appeal | Yard cleanup & front sod | 1500 | Front only
Landscaping & Curb Appeal | Fence repair/patch & stain | 900 | As needed
Landscaping & Curb Appeal
Contingency | 10% of estimated budget | 8500 |  | 0 | 0 | 0 | 0 | 0 | Draw Totals
|  |  |  | Total Budget | 93500
|  |  |  | Approved Draw Amount | 0
|  |  |  | Budget Remaining | 93500

## Blank Template
FixedLending — Scope of Work (Example — ~$90K Rehab with Draw Plan)
Property Address |  |  |  | Category Summary
Borrower Name |  |  |  | Demo & Prep | 0
Contractor Name |  |  |  | Foundation / Structure | 0
Project Type (Cosmetic/Light/Full) |  |  |  | Roof & Exterior | 0
Total SF |  |  |  | Interior Finishes | 0
Rehab Budget Target |  |  |  | Kitchen | 0
Scope Version |  |  |  | Bathrooms | 0
Date Reviewed |  |  |  | Mechanical Systems | 0
Approved By |  |  |  | Landscaping & Curb Appeal | 0
|  |  |  | Subtotal (All Categories) | 0
|  |  |  | Contingency (10%) | 0
|  |  |  | Estimated Total | 0
Category | Item | Total | Notes | Draw #1 | Draw #2 | Draw #3 | Draw #4 | Draw #5
|  |  |  | Date | Date | Date | Date | Date
Demo & Prep
Demo & Prep | Interior demo (walls/floors/cabs)
Demo & Prep | Dumpster & haul-off (30-yd)
Demo & Prep | Site cleanup / final broom
Foundation / Structure
Foundation / Structure | Foundation leveling/spot piers
Foundation / Structure | Structural beam/sill repair
Foundation / Structure | Framing (interior/exterior walls)
Foundation / Structure | Drywall install/finish
Foundation / Structure | Insulation (walls/attic)
Roof & Exterior
Roof & Exterior | Roof tear-off & replace (30-yr)
Roof & Exterior | Gutters & fascia repairs
Roof & Exterior | Exterior paint incl. trim
Roof & Exterior | Window replacements (vinyl DP) |  | (# of windows being replaced)
Roof & Exterior | Siding repair/replacement
Roof & Exterior | Concrete/driveway repair or replacement
Roof & Exterior | Garage door replace/install
Interior Finishes
Interior Finishes | LVP flooring install
Interior Finishes | Tile flooring install
Interior Finishes | Carpet install
Interior Finishes | Interior paint walls/trim/ceilings
Interior Finishes | Doors/trim install |  | (# of doors being replaced)
Interior Finishes | Hardware package
Interior Finishes | Lighting package (fans/cans/vanity)
Kitchen
Kitchen | Cabinets + install (shaker)
Kitchen | Countertops (quartz) + backsplash
Kitchen | Sink + faucet set
Kitchen | Appliance package (4pc)
Bathroom #1
Bathrooms | Bathtub
Bathrooms | Shower pan
Bathrooms | Flooring
Bathrooms | Vanity/Sink
Bathrooms | Toilet
Bathrooms | Fixtures/Finishes
Bathroom #2
Bathrooms | Bathtub
Bathrooms | Shower pan
Bathrooms | Flooring
Bathrooms | Vanity/Sink
Bathrooms | Toilet
Bathrooms | Fixtures/Finishes
Bathroom #3
Bathrooms | Bathtub
Bathrooms | Shower pan
Bathrooms | Flooring
Bathrooms | Vanity/Sink
Bathrooms | Toilet
Bathrooms | Fixtures/Finishes
Mechanical Systems
Mechanical Systems | HVAC system (3-ton) replace/serv
Mechanical Systems | Electrical panel/rough/finish
Mechanical Systems | Plumbing rough/trim + WH
Landscaping & Curb Appeal
Landscaping & Curb Appeal | Yard cleanup & front sod
Landscaping & Curb Appeal | Fence repair/patch & stain
Landscaping & Curb Appeal
Contingency | 10% of estimated budget | 0 |  | 0 | 0 | 0 | 0 | 0 | Draw Totals
|  |  |  | Total Budget | 0
|  |  |  | Approved Draw Amount | 0
|  |  |  | Budget Remaining | 0